## E and Q Documents
Expected Output Documents of both ECSS-E-ST-20-40 and ECSS-Q-ST-60-03
E-20-40 or Q-60-03 doc? | Document name | Document having a DRD annex | (DPR)DEVICE Definition Phase Review | (ADR)DEVICE Architecture Definition Phase Review | (DVR)DEVICE Design and Verification Phase Review | (DDR)DEVICE Detailed Design Phase Review | (LPR) DEVICE Layout Phase Review | (IPR) DEVICE Implementation Phase Review | (VQAR)DEVICE Validation, Qualification and Acceptance Phase Review | NOTATION: B = Configuration Baseline (as per ECSS-M-ST-40 clause 4.3.2.4) R = Review expected ECSS-E-ST-20-40 document outputs in blue font
E | DEVICE Requirements Specification (DRS) | ECSS-E-ST-20-40 Annex A | R
E | DEVICE Development Plan (DDP) | ECSS-E-ST-20-40 Annex B | R
E | DEVICE Verification Plan (DVeP) | ECSS-E-ST-20-40 Annex C | R | R | R
E | DEVICE Validation Plan (DVaP) | ECSS-E-ST-20-40 Annex D | R | R |  |  | R
E | DEVICE Support and Maintenance Plan (DSMP) (conditional) | ECSS-E-ST-20-40 Annex E | R | [5 empty] | R
E | DEVICE Feasibility and Risk Assessment Report (DFRAR) | ECSS-E-ST-20-40 Annex F | R | R | R | R | R | R | R
Q | DEVICE Product Assurance Plan (DPAP) | ECSS-Q-ST-60-03 Annex A | B
Q | DEVICE Product Assurance Report (DPAR) | ECSS-Q-ST-60-03 Annex B | R | R | R | R | R | R | R
Q | DEVICE Reuse File (DRF) | ECSS-Q-ST-60-03 Annex C | R | R | R | R | R | R | R
E | Verification Control Document (VCD) | ECSS-E-ST-10-02 Annex B | R | R | R | R | R | R | B
Q | Independent Verification Validation Plan (IVV Plan) |  | B
Q | Configuration Management Plan (CMP) | ECSS-M-ST-40 Annex A | B
Q | Configuration Item Data List (CIDL) | ECSS-M-ST-40 Annex C | B
E | DEVICE Architecture Definition Report | ECSS-E-ST-20-40 Annex G |  | R
E | DEVICE Design Report |  |  |  | R
E | DEVICE Design Verification Report |  |  |  | R
E | DEVICE Data Sheet (conditional) | ECSS-E-ST-20-40 Annex H |  |  | R | R | R | R | R
E | Netlist Generation Report |  |  |  |  | R
E | Netlist Verification Report |  |  |  |  | R
E | Layout Generation Report | [5 empty] | R
E | Layout Verification Report | [5 empty] | R
E | DEVICE Radiation Test Plan (conditional) | [5 empty] | R | R
E | ESCC Detail Specification (conditional) | [5 empty] | R | R | R
E | ASIC Production Tests Report or FPGA Programming Report | [6 empty] | R
E | DEVICE Validation report | [7 empty] | R
E | Radiation Test Report (conditional) | [7 empty] | R
E | DEVICE User Manual (conditional) | [7 empty] | R
E | Experience Summary Report (conditional) | ECSS-E-ST-20-40 Annex I | [6 empty] | R
Q | As-Built Configuration List (ABCL) | ECSS-M-ST-40 Annex D |  | R | R | R | R | R | B
Q | Software Configuration File (SCF) | ECSS-M-ST-40 Annex E | R | R | R | R | R | R | B
Q | Independent Verification Validation Report (IVV Report) |  | R | R | R | R | R | R | B
Q | End Item Data Pack (EIDP) | ECSS-Q-ST-20 Annex B | [6 empty] | B

## Engineering expected outputs
ECSS-E-ST-20-40 Table K-1: Summary of expected outputs of engineering flow
Development phase | Documentation | DEVICE models and SW | Hardware
DEVICE Definition Phase | DEVICE Requirements Specification (DRS)
DEVICE Feasibility and Risk Assessment Report (DFRAR)
DEVICE Development Plan (DDP)
DEVICE Verification Plan (preliminary) (DVeP)
DEVICE Validation Plan (preliminary) (DVaP)
DEVICE Verification Control Document (VCD)
DEVICE Support and Maintenance Plan (preliminary) (DSMP)
DEVICE Architecture Definition Phase | DEVICE Architecture Definition Report
DEVICE Requirements Specification (final) (DRS)
DEVICE Verification Plan (update) (DVeP)
DEVICE Validation Plan (update) (DVaP)
DEVICE Feasibility and Risk Assessment Report (update) (DFRAR)
DEVICE Verification Control Document (update) (VCD)
DEVICE Design and Verification Phase | DEVICE Design Report | DEVICE Database containing:
| DEVICE Design Verification Report | Simulation models (e.g. RTL)
| DEVICE Verification Control Document (update) (VCD) | Verification files
DEVICE Data Sheet (preliminary)
DEVICE Feasibility and Risk Assessment Report (update) (DFRAR)
DEVICE Verification Plan (final) (DVeP)
DEVICE Detailed Design Phase | Netlist Generation Report | Updated DEVICE database containing:
| Netlist Verification Report | Pre-layout netlist
| DEVICE Verification Control Document (update) (VCD) | Constraints for technology mapping and layout
| DEVICE Data Sheet (update) | Preliminary test vectors for ASIC Production Tests
DEVICE Feasibility and Risk Assessment Report (update) (DFRAR)
DEVICE Layout Phase | Layout Generation Report | Updated DEVICE database containing:
| Layout Verification Report | Post-layout netlist
| DEVICE Verification Control Document (update) (VCD) | parasitic effects information
| DEVICE Validation Plan (update) (DVaP) | ASIC files for manufacturer
| DEVICE Radiation Test Plan | FPGA programming files
| DEVICE Data Sheet (update) | Final ASIC Production Test Vectors
DEVICE Feasibility and Risk Assessment Report (update) (DFRAR)
ESCC Detail Specification (preliminary)
DEVICE Implementation Phase | ASIC Production Tests Report | Updated DEVICE database containing: | Tested DEVICE(s)
| FPGA Programming Test Report | Manufacturing or programming log and test files
DEVICE Verification Control Document (update) (VCD)
DEVICE Feasibility and Risk Assessment Report (update) (DFRAR)
DEVICE Validation Plan (final) (DVaP)
DEVICE Radiation Test Plan (final)
DEVICE Data Sheet (update)
ESCC Detail Specification (update)
DEVICE Validation, Qualification and Acceptance Phase | DEVICE Validation report | DEVICE Database (final) | Validation Tests hardware
| DEVICE Radiation Test Report | Validation Tests software and files | Validated DEVICE(s)
DEVICE Verification Control Document (final) (VCD)
DEVICE Data Sheet (final)
ESCC Detail Specification (final)
DEVICE User Manual
Experience Summary Report
DEVICE Support and Maintenance Plan (final) (DSMP)
DEVICE Feasibility and Risk Assessment Report (final) (DFRAR)